## Summary
ECI AI PLATFORM BUILD – ESTIMATION SUMMARY
Variables |  |  |  | Team Allocation |  |  |  | S.N. ¦ Pre-Requisites (Client Responsibility)
SNO | Variables | # |  | SNO | Role | Allocation % | Est. Days | 1 | Active Azure subscription with Contributor or Owner role at resource group level
1 | FrontEnd | No |  | SNO | Role | Allocation % | Est. Days | 2 | Microsoft 365 E3 (or higher) licenses for all service and user accounts
2 | Backend | Yes |  | 1 | Project Manager | 25% |  | 3 | Copilot Studio license (standalone ~$200/tenant/mo or via M365 tier — confirm with client)
3 | DevOps | Yes |  | 2 | AI Architect / Lead | 50% |  | 4 | Read/write SharePoint credentials and Graph API permissions for all source data
4 | QA | Yes |  | 3 | AI Engineer | 100% |  | 5 | Microsoft Teams admin consent for custom Copilot Studio bot deployment
5 | Mobile | No |  | 4 | QA Engineer | 50% |  | 6 | Azure AD user accounts provisioned for 10 POC users
Activities |  |  |  | 5 | DevOps Engineer | 25% |  | 7 | Identification of key stakeholders for workshops and UAT sign-off
SNO | Activities |  | DevTime (hrs) | 6 | Data Engineer | 50% |  | 8 | Access to all REST APIs and data sources listed in scope
1 | FrontEnd |  | 0 |  |  |  |  | 9 | Sample document corpus (50–100 files per use case) provided within 1 week of kickoff
2 | Backend | [6 empty] | 10 | Agreed document template formats locked before ingestion begins
3 | DevOps |  |  | Monthly Infra Cost (Est.)
S.N. ¦ Out of Scope
| Component | Days | Weeks |  |  |  |  | 1 | Data ingestion from sources outside the agreed list (non-approved data)
| FrontEnd | 0 | 0 |  |  |  |  | 2 | Automated real-time ingestion — only one-time + scheduled delta ingestion in scope
| Backend | [6 empty] | 3 | Custom UI development outside Teams (no web portal or mobile app)
| DevOps | [6 empty] | 4 | Building full CI/CD pipelines or advanced release automation
Project Duration | [7 empty] | 5 | PowerPoint (.pptx) and image files as primary data source types
[8 empty] | 6 | Long-term AI operations support beyond the 30-day stabilisation period
Project Duration including Leaves & Holiday | [7 empty] | 7 | Unstructured formats like audio and video not supported as data sources
| Leaves & Holiday | 1 | Weeks |  |  |  |  | 8 | Multi-language support beyond English + 1 additional language
|  |  | Weeks |  |  |  |  | 9 | Real-time external data feeds (market data, live APIs beyond what is listed)
Note: With 2 AI Engineers, project can be completed within 8-10 weeks. | [7 empty] | 10 | Any new features or requests not mentioned in scope (change request process applies)
S.N. ¦ Assumptions
[8 empty] | 1 | Source files are PDF, Word, and Excel only — all other formats excluded unless specifically agreed
[8 empty] | 2 | 50–100 historical files per use case will be provided within POC scope
[8 empty] | 3 | AI response accuracy is estimated at 80–95% for structured queries. 100% accuracy is not guaranteed.
[8 empty] | 4 | AI responses are advisory in nature — all outputs must be reviewed and validated by client before decisions.
[8 empty] | 5 | Model accuracy is dependent on quality, consistency, and completeness of source files provided.
[8 empty] | 6 | A single agreed-upon document template per use case will be confirmed and locked during Discovery & Design.
[8 empty] | 7 | One-time ingestion plus scheduled delta sync; no real-time streaming ingestion.
[8 empty] | 8 | 10 users will participate in UAT, each testing 50–100 queries across all 3 use cases.
[8 empty] | 9 | Users must have existing SharePoint and Teams access to use the agent.
[8 empty] | 10 | Prompt logs stored in Azure Monitor / Log Analytics with 90-day default retention.
[8 empty] | 11 | Existing Azure landing zone and subscription will be leveraged — no new subscription required.
[8 empty] | 12 | Client is responsible for all Azure/cloud licensing, infrastructure, and data usage costs.
[8 empty] | 13 | Client will assign UAT resource(s) and respond to ECI queries within 24–48 hours.
[8 empty] | 14 | The UAT phase will follow a set timeline; no new enhancements during UAT.
[8 empty] | 15 | Data classification and labeling not required for the POC phase.
S.N. ¦ Risks
[8 empty] | 1 | API restrictions: Permission or access issues may add significant effort — validate in Discovery.
[8 empty] | 2 | LLM hallucination risk: Without human review, incorrect AI outputs could influence real decisions.
[8 empty] | 3 | File volume unvalidated: 50–100 files/use case is an estimate; insufficient data may impact KPI validation.
[8 empty] | 4 | Document inconsistency: Varying formats across analysts will degrade AI accuracy.
[8 empty] | 5 | Scope creep: Use cases may expand to additional reports or data types during UAT — change request process applies.
[8 empty] | 6 | Model performance variability: GPT-4o vs GPT-4o-mini quality gap may require additional prompt tuning.
[8 empty] | 7 | Delta sync complexity: Incremental ingestion logic may require additional effort if source structure changes.
[8 empty] | 8 | Copilot Studio licensing: Cost depends on client M365 tier — standalone ~$200/tenant/mo; confirm before start.
[8 empty] | 9 | Prompt log retention: Retention beyond 90 days requires additional configuration and may impact cost.
[8 empty] | 10 | Teams deployment approval: Bot deployment to tenant requires admin consent — delays possible.
S.N. ¦ Definition of Done – Project Closure Criteria
► DISCOVERY & DESIGN
[8 empty] | 1 | Technical architecture document reviewed and signed off by client stakeholders
[8 empty] | 2 | KPI metrics and acceptance thresholds defined, documented, and agreed upon by both parties
[8 empty] | 3 | All data source access confirmed and tested (SharePoint, REST APIs, SQL)
[8 empty] | 4 | Prompt templates provided and approved for all 3 use cases
► ENVIRONMENT SETUP
[8 empty] | 1 | All Azure resources provisioned: Resource Group, VNet, AI Foundry, AI Search, App Service, Key Vault, Azure Monitor
[8 empty] | 2 | Entra ID / Azure AD app registrations and service principals created with least-privilege access
[8 empty] | 3 | Copilot Studio bot deployed to client's Teams tenant with admin consent granted
► DATA INGESTION
[8 empty] | 1 | One-time ingestion completed for all 3 use cases — files validated and indexed in Azure AI Search
[8 empty] | 2 | Two embedding models tested; embeddings stored and validated
[8 empty] | 3 | Hybrid search (vector + BM25) confirmed functional via representative test queries
[8 empty] | 4 | Azure SQL metadata store populated and validated
[8 empty] | 5 | Delta sync trigger configured and tested
► AI AGENT
[8 empty] | 1 | All 3 use case pipelines returning relevant responses meeting KPI thresholds
[8 empty] | 2 | Multi-model comparison completed: GPT-4o vs GPT-4o-mini evaluated across defined KPIs
[8 empty] | 3 | Prompt logging active — all interactions captured in Azure Monitor (90-day retention confirmed)
[8 empty] | 4 | Adaptive Card trigger and Teams bot responses functional for all 3 use cases
► TESTING & UAT
[8 empty] | 1 | All unit and integration tests passing with minimum critical defects
[8 empty] | 2 | 10 POC users completed UAT (50–100 queries each) across all 3 use cases
[8 empty] | 3 | Security testing passed: authentication, authorization, data isolation verified
[8 empty] | 4 | Feedback incorporated and sign-off obtained from UAT participants
► PRODUCTION DEPLOYMENT & HANDOVER
[8 empty] | 1 | Production environment deployed, smoke tested, and monitoring alerts configured
[8 empty] | 2 | Architecture documentation and user guides finalized and delivered to client
[8 empty] | 3 | Production access credentials transferred with least-privilege RBAC
[8 empty] | 4 | Runbook delivered to operations team

## AI Agent Dev- Backend
ECI AI PLATFORM BUILD – AI AGENT DEVELOPMENT & INTEGRATION
# | Task / Phase | Sub-task | Dev Low (hrs) | Dev High (hrs) | Avg (hrs) | Comments
Phase 1: Discovery & Design
1 |  | Project kickoff, scope alignment & stakeholder mapping | 10 | 14 |  | Workshops with business & tech leads
2 |  | Existing system & data source review (APIs, DBs, file stores) | 8 | 12 |  | Audit current integrations & data quality
3 |  | 50–100 document sample analysis (PDFs, Word, Excel) | 8 | 12 |  | Validate content types and metadata structure
4 |  | Solution architecture finalization & sign-off | 6 | 8 |  | Private endpoint, cloud landing zone design
5 |  | Technical design documentation (HLD + LLD) | 12 | 16 |  | Architecture & data flow diagrams
6 |  | Prompt engineering design for all use cases | 8 | 12 |  | Use-case specific prompt templates
7 |  | KPI metric & threshold definition | 6 | 10 |  | Accuracy, latency, relevance benchmarks
8 |  | Data governance & compliance review | 4 | 6 |  | GDPR / data residency checks
9 |  | Risk assessment & mitigation plan documentation | 4 | 6 |  | Risk register creation
Phase 2: Data Ingestion & Processing Pipeline
10 |  | Connector setup for source systems (REST API, SharePoint, SQL) | 8 | 12 |  | One-time ingestion pipeline per source
11 |  | PDF/Word/Excel parsing, extraction & metadata tagging | 10 | 14 |  | Multi-format document processing
12 |  | Intelligent chunking strategy & overlap configuration | 6 | 10 |  | Optimised for RAG retrieval accuracy
13 |  | Azure OpenAI embedding integration (2 embedding models) | 14 | 18 |  | text-embedding-3-large + ada-002
14 |  | One-time embedding generation for all source documents | 12 | 16 |  | Full corpus vectorisation
15 |  | Azure AI Search schema design + hybrid search config | 16 | 22 |  | Vector + BM25 keyword hybrid index
16 |  | Azure SQL metadata store design & population | 6 | 10 |  | Structured lookup tables
17 |  | Data validation & ingestion QA | 4 | 6 |  | Spot-check retrieval quality
18 |  | Automated re-ingestion trigger (delta updates) | 6 | 10 |  | Scheduled incremental sync
Phase 3: AI Agent Development
19 |  | Use Case 1: Document Q&A – prompt engineering & RAG pipeline | 10 | 14 |  | Natural language Q&A over enterprise docs
20 |  | Use Case 1: Contextual answer generation with citation | 10 | 14 |  | Source attribution for every response
21 |  | Use Case 1: Adaptive Card trigger & response formatting (Teams) | 6 | 8 |  | Trigger via Teams; output as rich card
22 |  | Use Case 2: Intelligent Report Summarisation – RAG pipeline | 10 | 14 |  | Auto-summarise lengthy reports
23 |  | Use Case 2: Multi-document synthesis & comparison logic | 8 | 12 |  | Cross-document insights
24 |  | Use Case 2: Structured summary output & export (Word/PDF) | 6 | 8 |  | Formatted downloadable summaries
25 |  | Use Case 3: Anomaly & Insight Detection from structured data | 8 | 12 |  | Flag outliers, trends & exceptions
26 |  | Multi-model evaluation – GPT-4o vs GPT-4o-mini + 2 embedding models | 6 | 8 |  | Compare quality vs cost
27 |  | Prompt logging (Azure Monitor / Log Analytics) | 4 | 6 |  | Full audit trail
28 |  | Security controls – Key Vault, Entra ID managed identity | 4 | 8 |  | Least-privilege per-user controls
29 |  | Rate limiting & user authorisation (10 POC users) | 4 | 6 |  | Azure AD group-based access
30 |  | Conversation memory & session management | 4 | 6 |  | Short-term context retention
Phase 4: Teams Bot Development (Copilot Studio)
31 |  | Backend REST API (FastAPI) – bot orchestration layer | 10 | 14 |  | Query routing to AI agent
32 |  | Azure AD / Entra SSO integration | 4 | 6 |  | Teams identity & service principal
33 |  | Copilot Studio bot config & Teams channel publishing | 6 | 8 |  | Teams bot channel deployment
34 |  | Adaptive cards / rich response formatting (all 3 use cases) | 6 | 8 |  | Structured output per use case
35 |  | Feedback collection & thumbs-up/down logging | 4 | 6 |  | User satisfaction tracking
36 |  | End-to-end conversation flow testing | 4 | 8 |  | Validate all use case flows in Teams
37 |  | Multi-language support configuration (English + 1 additional) | 4 | 6 |  | Locale-aware prompts
Phase 5: Testing & UAT
38 |  | Unit testing – all agent components | 6 | 10 |  | Function-level tests for all use cases
39 |  | Integration testing – end-to-end workflow (all 3 use cases) | 8 | 12 |  | Source → Agent → Teams validation
40 |  | Prompt engineering tuning (all use cases) | 8 | 12 |  | Optimise against KPI thresholds
41 |  | Performance testing – response time target <8s | 4 | 6 |  | 10 concurrent users simulation
42 |  | Security testing – auth, authorisation, data isolation | 4 | 6 |  | Pen-test checklist
43 |  | UAT coordination with 10 users (50–100 queries each) | 4 | 6 |  | Real queries across all use cases
44 |  | Accessibility & UX review of Teams adaptive cards | 2 | 4 |  | WCAG 2.1 AA compliance check
45 |  | Feedback incorporation & bug fixes | 6 | 8 |  | Address UAT findings
Phase 6: Production Deployment & Handover
46 |  | Architecture documentation with diagrams (HLD + LLD) | 4 | 6 |  | Technical design docs delivered
47 |  | User guide creation (with screenshots & video walkthroughs) | 4 | 6 |  | End-user how-to guide for all use cases
48 |  | End-user training sessions (2 × 2 hrs, recorded) | 4 | 4 |  | How to use Teams bot for all use cases
49 |  | Runbook for ops team (monitoring, alerts, re-ingestion) | 2 | 4 |  | Operational handover guide
50 |  | Production cutover, smoke testing & go-live sign-off | 2 | 4 |  | Final deployment validation
Project Management (10% of dev hours) | [5 empty] | Throughout project
TOTAL PROJECT HOURS | [5 empty] | Average hours noted for reference

## DevOps
ECI AI PLATFORM BUILD – DEVOPS & INFRASTRUCTURE PROVISIONING
# | Task / Phase | Sub-task | Dev Low (hrs) | Dev High (hrs) | Avg (hrs) | Comments
Azure Environment Setup
1 |  | Azure Resource Group, VNet & Subnets provisioning | 2 | 3 |  | Isolated network foundation
2 |  | Private endpoints & Private Link config (all services) | 8 | 12 |  | All services off public internet
3 |  | Azure AI Foundry workspace setup & model deployments | 4 | 6 |  | GPT-4o + GPT-4o-mini + embedding models
4 |  | Azure AI Search instance (Standard S1) provisioning | 2 | 4 |  | Vector + keyword hybrid search
5 |  | Azure App Service (P2V3) for bot backend | 2 | 3 |  | REST API hosting for FastAPI backend
6 |  | Azure Key Vault & secrets configuration | 2 | 4 |  | API keys, credentials, managed identity
7 |  | Azure Monitor + Log Analytics (90-day retention) | 2 | 3 |  | Prompt logging & observability
8 |  | Azure SQL Database (Standard S3) provisioning | 3 | 4 |  | Structured metadata & audit log storage
9 |  | Azure Blob Storage (LRS) for document staging | 2 | 3 |  | Temp staging & processed doc archive
10 |  | SharePoint & REST API service principal configuration | 3 | 4 |  | Auth for all data source connectors
11 |  | Entra ID / Azure AD app registrations | 2 | 3 |  | Auth for APIs & Teams bot
12 |  | Azure Front Door / API Management (optional WAF layer) | 3 | 5 |  | Rate limiting, WAF rules
Copilot Studio & Teams Integration
13 |  | Copilot Studio environment provisioning & bot channel setup | 3 | 5 |  | Teams bot channel configuration
14 |  | Teams admin consent & bot deployment to tenant | 3 | 5 |  | Admin approval required
Security Baseline & Testing
15 |  | NSG rules, Azure AD conditional access, Key Vault policies | 4 | 6 |  | Security hardening per scope
16 |  | UAT staging environment deployment | 2 | 3 |  | Mirror of production
17 |  | RBAC configuration – least-privilege roles per team member | 2 | 3 |  | PIM-based access review
Meetings & Sync (10% of dev hours) | [5 empty] | Standups, client syncs
TOTAL DEVOPS HOURS | [5 empty] | Average for budgeting

## Architecture
ECI AI PLATFORM BUILD – SOLUTION ARCHITECTURE
Platform | Microsoft Azure (existing subscription leveraged)
AI Engine | Azure OpenAI – GPT-4o (primary) + GPT-4o-mini (cost optimisation)
Vector Store | Azure AI Search Standard S1 – hybrid (vector + BM25)
Embeddings | text-embedding-3-large + text-embedding-ada-002
Bot Channel | Copilot Studio → Microsoft Teams
Backend API | FastAPI on Azure App Service P2V3
Auth | Azure AD / Entra ID – managed identity, SSO
Data Sources | SharePoint Online, REST APIs, Azure SQL, Azure Blob Storage
Monitoring | Azure Monitor + Log Analytics (90-day retention)
Security | Azure Key Vault, Private Endpoints, NSG, Conditional Access
Use Case 1 – Document Q&A · Natural language question answering over enterprise documents (PDFs, Word, Excel) via Azure AI Search + GPT-4o RAG pipeline · Teams Adaptive Card trigger → Text + citation output
Use Case 2 – Intelligent Report Summarisation · Automated multi-document synthesis & comparison with structured downloadable summary (Word/PDF) · Teams agent search → Formatted summary output
Use Case 3 – Anomaly & Insight Detection · Structured data analysis flagging outliers, trends and exceptions across connected data sources · Teams notification → Dashboard-ready insight cards

## Infra Cost
ECI AI PLATFORM BUILD – INFRASTRUCTURE COST ESTIMATE
# | Service / Resource | $/mo | Pricing Model | Notes / Assumptions
AI Services — Azure AI Foundry / OpenAI
1 | GPT-4o (Primary LLM — 85% of queries) | 35 | Pay-per-token | ~750 queries/mo avg 1,200 input + 600 output tokens. GPT-4o: $2.50/$10 per 1M tokens. ~85% of queries.
2 | GPT-4o-mini (Cost-optimised — 15% of queries) | 5 | Pay-per-token | ~135 queries/mo comparison testing. GPT-4o-mini: $0.15/$0.60 per 1M tokens.
Subtotal — AI Services
Vector Storage — Azure AI Search
3 | Azure AI Search — Standard S1 (1 replica, 1 partition) | 245 | Fixed monthly | S1 required for semantic ranker + hybrid search. ~$245/mo base. Supports all 3 use case indexes.
Subtotal — Vector Storage
Compute — App Service & Functions
4 | Azure App Service — P2V3 Linux (FastAPI backend / Teams bot) | 80 | Fixed monthly | P2V3: 2 vCPU, 8 GB RAM. ~$80/mo. Hosts REST API for Copilot Studio bot.
5 | Azure Functions — Consumption Plan (ingestion helper) | 5 | Pay-per-execution | Used during SharePoint ingestion & delta sync. Near-zero ongoing cost.
6 | Azure Blob Storage — LRS (document staging & archive) | 10 | Pay-per-GB | ~20 GB document corpus + staging. $0.018/GB/mo.
Subtotal — Compute
Database — Azure SQL
7 | Azure SQL Database — Standard S3 (100 DTUs) | 150 | Fixed monthly | S3 = 100 DTUs. Metadata queries, audit logs and cap rate lookup tables. Private endpoint included.
Subtotal — Database / Azure SQL
Security & Identity
8 | Azure Key Vault (secrets, API keys, managed identity) | 10 | Operations-based | Standard tier. ~15K operations/mo. First 10K ops free, then $0.03/10K.
9 | Entra ID / Azure AD (service principals, app registrations) | 0 | Included in M365 E3 | No additional cost. 10 POC users on existing E3 licences.
10 | Azure Front Door / API Management (WAF + rate limiting) | 50 | Fixed monthly | Developer tier API Management. WAF policy + IP filtering.
Subtotal — Security & Identity
Monitoring & Observability
11 | Azure Monitor — Log Analytics Workspace | 35 | Per GB ingested | Prompt logs for all interactions. ~3-5 GB/mo. $2.30/GB after 5 GB free tier.
12 | Azure Monitor — Alerts & Dashboards | 5 | Per alert rule | 10 alert rules for latency, error rate, ingestion status.
Subtotal — Monitoring & Observability
Integration — Copilot Studio & Teams
13 | Copilot Studio (Teams bot, Adaptive Cards – all 3 use cases) | 200 | Pay per message / tenant | ~$200/tenant/mo standalone OR depends on M365 licence tier. Confirm with client.
Subtotal — Integration
TOTAL ESTIMATED MONTHLY INFRASTRUCTURE COST |  |  |  | Estimated monthly cost for POC environment. Excludes one-time setup costs and Copilot Studio (confirm licence with client).

## Version History
VERSION HISTORY
Version | Changes | Date | Author
v1.0 | Initial estimate based on ECI AI Platform scope document | 2026-03-11 | Prabhakar